## proj21013-tracker51362-20150628
GRAHAM TECHNOLOGIES, LLC
Priority | Backlog Task | Assigned To | Status | Category
4 | TeamForge contributor permissions | William Graham | Done | Configuration
4 | Analyze Requirements for Technologies | William Graham | Done | Research
4 | Test Read functionality of the REST Service for the Local DB | Rodney Morris | Done | Test
4 | Create GitHub Project | None | Done | Configuration
4 | Create GitHub Branches | William Graham | Done | Configuration
2 | Provide Read Locally REST Service | Rodney Morris | Done | Code
4 | Test Update functionality of the REST Service for the Local DB | Rodney Morris | Done | Test
4 | Create a TeamForge Project | None | Done | Configuration
4 | Invite TeamForge Contributors | William Graham | Done | Configuration
4 | Install and Configure Tomcat | Brian Thompson | Done | Configuration
2 | Consume FedData REST Service | Rodney Morris | Done | Code
4 | Install and Configure Maven | Brian Thompson | Done | Configuration
4 | Install and Configure Java JDK | Brian Thompson | Done | Configuration
4 | Configure Maven Deployment Automation | Rodney Morris | Done | Build
2 | Display Items from Application | Frank Goodman | Done | Code
4 | Create Team Forge Agile Folder Structure | William Graham | Done | Configuration
3 | Configure the CI Tool for Automation | Brian Thompson | Done | Deploy
2 | Provide Update Locally REST Service | Rodney Morris | Done | Code
4 | Assign GitHub Contributor Permissions | William Graham | Done | Configuration
4 | AWS Integration Environment Provision | Brian Thompson | Done | Configuration
4 | Install and Configure Apache Web Server | Brian Thompson | Done | Configuration
4 | Test Read functionality of the REST Service for the external data consumption | Rodney Morris | Done | Test
4 | Post TeamForge Documentation | William Graham | Done | Configuration
4 | Invite GitHub Contributors | William Graham | Done | Configuration
4 | Configure GitHub Contributor Permissions | William Graham | Done | Configuration
4 | Install and Configure Monit | Brian Thompson | Done | Configuration
3 | Configure Continuous Monitoring UI | Brian Thompson | Done | Build
3 | Identify Resumes for Labor Categories | LaToya Graham | Done | Research
3 | Document All Technologies and their License Status | Brian Thompson | Done | Configuration
3 | Create Prototype ReadMe | William Graham | Done | Configuration
2 | Configure TeamForge Agile Management System | William Graham | Done | Configuration
4 | Provide Delete Locally REST Service | Rodney Morris | Done | Code
4 | Provide Create Locally REST Service | Rodney Morris | Done | Code
4 | Configure Continuous Monitoring Alerts | Brian Thompson | Done | Configuration
4 | Test Create functionality of the REST Service for the Local DB | Rodney Morris | Done | Test
4 | Test Delete functionality of the REST Service for the Local DB | Rodney Morris | Done | Test
4 | Configure IDEs with GitHub | Rodney Morris | Done | Configuration
4 | Assign TeamForge Contributor Permissions | William Graham | Done | Configuration
4 | AWS Production Environment Provision | Brian Thompson | Done | Configuration
4 | Install and Configure Ubuntu OS | Brian Thompson | Done | Configuration
4 | Install and Configure Eclipse | Brian Thompson | Done | Configuration
4 | Install and Configure MySQL | Brian Thompson | Done | Configuration
4 | Install and Configure Jenkins CI | Brian Thompson | Done | Configuration
4 | Install and Configure Git | Brian Thompson | Done | Configuration
4 | Assign Resources to Prototype | LaToya Graham | Done | Research
4 | Create Item in Application | Frank Goodman | Done | Code
4 | Delete Items from Application | Frank Goodman | Done | Code
2 | Update Items from Application | Frank Goodman | Done | Code
4 | Technology Selection for Prototype | William Graham | Done | Research
4 | Allocate Hours for Resources | LaToya Graham | Done | Research